## Functional Requirements
Last Updated On | Workshop ID | Business Process | Req. ID | Requirement | Worshop Discussion | Requirement Met (Y/N) | RICEF | Solution | Design Document Reference | Build Details | Status
|  | General | FNR 1.1 | The system shall provide an English user interface for the system to be used in Sweden | Seems like a direct requirement, not discussed in the Workshop | Y | C
|  | General | FNR 1.2 | The supplier shall provide an Danish or English user interface for the system to be used in Denmark | Seems like a direct requirement, not discussed in the Workshop | Y | C | Will provide user interface in Eng and Danish
|  | General | FNR 1.3 | The system shall include error logging functionality to facilitate root-cause detection for effective issue resolution. (The minimum information that is expected to be logged is, Timestamp: The exact date and time when the error occurred, Error Description: A clear description of the error, including any error codes or messages, Context Information: Relevant data about the state of the system when the error occurred, such as user actions, system events, or processes running) | Seems like a direct requirement, not discussed in the Workshop | Y | C | RFP
|  | General | FNR 1.4 | In the event of an application error, the system shall present a notification to the user detailing the time of the error and a concise description. If a resolution step is applicable, it will be included; otherwise, contact information for support will be provided. The notification will include an acknowledgement option to ensure the user can confirm receipt and continue with their tasks. | Seems like a direct requirement, not discussed in the Workshop | Y | C | RFP
|  | General | FNR 1.5 | The system shall implement Role-Based Access Control (RBAC) to grant distinct user groups tailored access to specific functional modules or features based on their roles and responsibilities. The RBAC system must include a set of standard predefined roles with clear descriptions and also provide the capability for administrators to create and manage custom roles. Additionally, the system must support users being assigned multiple roles to accommodate complex access needs. Supplier and Ørsted must apply least privilege principles ensuring that each role is only configured with the necessary rights to perform the task | Seems like a direct requirement, not discussed in the Workshop | Y | C | Template will be delivered to Orsted which will have the details of Orsted users and their profiles.
|  | General | FNR 1.6 | Ørsted wishes to be able to define and create user groups. | Seems like a direct requirement, not discussed in the Workshop | Y | C | RFP
|  | Customer Master Data | FNR 2.1 | The system shall be possible to get data from Ørsteds Danish Billing System (Easy Energy) and the Swedish Billing System (BFUS) and Ørsted CRM (Salesforce). (See appendix NFR_App_1_Billing Data Integration, where the data ingested from the Billing systems is defined). | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Customer Master Data | FNR 2.2 | Ørsted wishes to have data exchange from Ørsteds Danish Billing System (Easy Energy) and the Swedish Billing System (BFUS) and CRM systems to happen automatically | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Customer Master Data | FNR 2.3 | The system must enable users to perform manual imports of metering point data via an external CSV file upload feature. (CSV shall be supported at least) | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Customer Master Data | FNR 2.4 | Ørsted shall be able to create and modify and remove a customizable customer hierarchy, ensuring adaptability to accommodate future organizational changes and strategies. (See appendix FR_App_2 Ørsted Customer hierarchy, for an illustration of the current costumer hierarchy). | Seems like a direct requirement, not discussed in the Workshop | Y |  | Account hierarchy is managed within Salesforce CRM and inherited in CPQ. The hierarchy can be therefore used within the CPQ to manage business logics. Bit2win's CPQ experience (UX) is seemlessly embedded into SFDC through the use of Lightning Web Components.
|  | Customer Master Data | FNR 2.5 | The system shall support the ability to load metering point information, comprising realized hourly consumption and at the lowest graduality available, expected annual consumption, customer numbers, payer address, etc., (uploaded manually from end user device ) | Seems like a direct requirement, not discussed in the Workshop |  |  | Pricing
|  | Customer Master Data | FNR 2.6 | The system shall support meter point time information always at the lowest granularity provided by the national grid operators for both Denmark and Sweden | Seems like a direct requirement, not discussed in the Workshop |  |  | Pricing
|  | Metering Point Consumption Data | FNR 3.2 | The system shall support a daily automated load of the latest available consumption data for each metering point included in a customer contract. It must be at the lowest level of granulation and be ready for the Danish and Swedish change of regime to quarter hours. | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Metering Point Consumption Data | FNR 3.4 | The system shall support the ability to source the metering point data from the relevant data source. It can either be a datahub of the like or directly from the national/regional grid operator. (e.g. For Denmark Datahub for Power and Evida for Gas) | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Metering Point Consumption Data | FNR 3.5 | The system must enable users to import historical hourly consumption profiles from an external file (at least CSV file format should be supported) through the user interface and assign these profiles to a specific metering point and customer. | Seems like a direct requirement, not discussed in the Workshop |  |  | Integration Workshop data
|  | Metering Point Consumption Data | FNR 3.6 | Ørsted wishes to explore the automatic ingestion of historic consumption profile | Seems like a direct requirement, not discussed in the Workshop |  |  | DM Srategy
| Forecast Logic | Metering Point Consumption Data | FNR 3.7 | The system must allow the users to link the uploaded consumption profiles to a standard profile that corresponds to a particular industry sector | Seems like a direct requirement, not discussed in the Workshop |  |  | Forcasting/Pricing
|  | Metering Point Consumption Data | FNR 3.8 | The system shall accommodate the inclusion and management of production metering points. This will enable Ørsted to account for and process energy production data, irrespective of the energy source, ensuring that customers with energy-producing capabilities, such as solar panels, wind turbines, or other renewable sources, are properly managed within the system. | Need to add in Integration doc- Ajeesh |  |  | Integration Strategy
| W5 | Opening and Closing Possibility for Offers and Contracts | FNR 4.1 | The system must provide a feature that allows a designated group of users to activate or deactivate the sales time frame for specific sales segments during the offering and contracting process.
| W5 | Opening and Closing Possibility for Offers and Contracts | FNR 4.2 | The system shall display commodity (power, gas & green certificates) market forward prices for each delivery month, ranging from front-month to rest-of-year and 5 years ahead. This information shall be available for Gas (Denmark and Sweden) and each price area for Power (Denmark). The interface to obtain prices is detailed in Appendix NFR_App_4_PREP Integration.
| W5 | Opening and Closing Possibility for Offers and Contracts | FNR 4.3 | The system should provide the users the ability to download the displayed prices in a file format in their local device (CSV format should be supported as minimum).
| W4 | Fee Management | FNR 5.1 | The system shall enable user-defined fee configuration, with the flexibility to apply these fees to chosen products or uniformly across the entire product range.
| W4 | Fee Management | FNR 5.2 | Ørsted wishes that system should support the fee configuration in a flexible manner.
| W4 | Fee Management | FNR 5.3 | The system shall be able to assign a unique identifier for each fee.
| W4 | Fee Management | FNR 5.4 | The system shall provide the ability for the Users to choose between different fee types: - fixed (value manually entered by super-user) - curve-based (user indicated ID related to a price curve defined in PREP = Ørsted price database) - multi-value (user can choose a fee from an option list, where one of the options is the "active" one currently used to handle different RE assets one can choose when specifying Guarantee of origin (GO) cost) - multi-curve (same principle as multi-value, but here are the options not values, but IDs referring to a PREP price curve)
| W4 | Fee Management | FNR 5.5 | Ørsted wishes for suppliers to describe all the available fee types that their solution can support.
| W4 | Fee Management | FNR 5.6 | Each fee shall have configurable parameters, determining its applicability in a given offer, justification by a user, and whether it is included in the contract price or specified separately.
| W4 | Fee Management | FNR 5.7 | Volume units, including "øre/m³" for gas DK, "øre/kWh(n)" for gas SE and "øre/kWh" for power DK, as well as fixed amounts per month/year and amount/meter, shall be configurable within the system.
| W4 | Fee Management | FNR 5.8 | The system shall be able to handle multiple currencies at least both SEK & EUR for Sweden (one specific currency for one specific contract)
| W4 | Fee Management | FNR 5.9 | The system shall be able to handle multiple currencies at least both DKK & EUR for Denmark & SEK (one specific currency for one specific contract)
| W4 | Fee Management | FNR 5.10 | The system shall have the capability to automatically import fees such as national gas transmission tariffs and volume flexibility fees for fixed price energy products, as well as capacity payment fees for customers with hourly-measured energy consumption, from external systems.
| W4 | Fee Management | FNR 5.11 | The system must be designed to integrate seamlessly with external systems responsible for the calculation of the aforementioned fees in FNR 5.10, ensuring secure, reliable data exchange without manual intervention. (See Appendix NFR_App_3_Hadrian Integration).
| W4 | Fee Management | FNR 5.12 | The system must be capable of handling two sets of Energinet tariffs for two different delivery years simultaneously to accommodate contracts that span across calendar years.
| W4 | Fee Management | FNR 5.13 | The system shall enable manual entry of Energinet gas transmission tariffs for annual, quarterly, monthly, and daily booking periods.
| W2 | Product Management | FNR 6.1 | The system shall facilitate the configuration of products, including the assignment of pertinent fees, associated sales channels, product/hedge portfolios, price validity (EoD, next day, EoM), and templates for offer/contract text. |  |  | C | Bit2Win manages product design, including creating complex and simple products, configuring sales, associating pricelists, and adding families and attributes. | https://wipro365.sharepoint.com/:w:/r/sites/Orsted-Bit2winTeam/Shared%20Documents/Orsted%20project%20team/FDD/Product%20Management/Orsted%20-%20Review%20comments/FDD_ProductManagement%20-%20v0.2.docx?d=wfe87f883a75b4525a56178df4bd3c41a&csf=1&web=1&e=fSu0h7 |  | Agreed
| W2 | Product Management | FNR 6.2 | The system will provide functionality allowing a designated user group to activate or deactivate specific products according to their discretion. Products that are marked as 'activated' will be eligible for selection for offers. Conversely, products that are deactivated will not be available for inclusion in offers until reactivated by authorized users |  |  | C | This will be managed in Bit2win OOB feature where user will be able to change the start and End date of the products to activate or deactivate according to their discretion | https://wipro365.sharepoint.com/:w:/r/sites/Orsted-Bit2winTeam/Shared%20Documents/Orsted%20project%20team/FDD/Product%20Management/Orsted%20-%20Review%20comments/FDD_ProductManagement%20-%20v0.2.docx?d=wfe87f883a75b4525a56178df4bd3c41a&csf=1&web=1&e=fSu0h8 |  | Agreed
| W2 | Product Management | FNR 6.3 | The system shall calculate the commodity price for fixed-price power contracts in Denmark (DK1 or DK2 areas) as a weighted average of the monthly hedges, which are to be determined based on the customer-specific contracted consumption profile. This calculation must differentiate between base and peak hedge volumes, priced respectively at base and peak rates, with the base/peak hedge ratio defined by Ørsted's proprietary formula. |  |  | C | This will be managed in Bit2win with the "Rule Engine" that can read the customer's consumption curve and apply prices after performing the necessary calculations. Details related to price curves and calculations are described in Pricing FDD. | Pricing FDD |  | Agreed
| W2 | Product Management | FNR 6.4 | The system shall calculate the commodity price for fixed-price gas contracts in Denmark and Sweden as a weighted average of the monthly hedges, tailored to hedge the customer-specific contracted consumption profile. |  |  | C | Details related to hedging and calculations are described in Pricing FDD | Pricing FDD |  | Agreed
| W2 | Product Management | FNR 6.5 | The system shall support as minimum the following products that Ørsted has defined - Spot price - Fixed Price - Fixed Price Combi - Commodity+ The specific requirements for each product are provided in Appendix FR_App_1 Ørsted Pricing Products. | To review and confirm the description of functional requirement from Orsted |  | C | The Bit2win system supports all the mentioned products and the has product configurations | https://wipro365.sharepoint.com/:w:/r/sites/Orsted-Bit2winTeam/Shared%20Documents/Orsted%20project%20team/FDD/Product%20Management/Orsted%20-%20Review%20comments/FDD_ProductManagement%20-%20v0.2.docx?d=wfe87f883a75b4525a56178df4bd3c41a&csf=1&web=1&e=fSu0h11 |  | Pending
| W2 | Product Management | FNR 6.6 | The system shall be adaptable and scalable to ensure compatibility with any new products Ørsted may introduce in the future. (E.g. Power Products for the Swedish market) |  |  | C | Orsted will be able to configure new products as per the user privilege | https://wipro365.sharepoint.com/:w:/r/sites/Orsted-Bit2winTeam/Shared%20Documents/Orsted%20project%20team/FDD/Product%20Management/Orsted%20-%20Review%20comments/FDD_ProductManagement%20-%20v0.2.docx?d=wfe87f883a75b4525a56178df4bd3c41a&csf=1&web=1&e=fSu0h12 |  | Agreed
| W6 | Offer and Contract Document Administration | FNR 7.1 | The system shall support the creation of templates for offer/contract document text.
| W6 | Offer and Contract Document Administration | FNR 7.2 | The system shall offer the capability to users to create and relate products to appendices (When that product is chosen the related appendix is attached to the contract).
| W6 | Offer and Contract Document Administration | FNR 7.3 | Ørsted wishes the system to be able to support the functionality of adding appendices in the contract, with the capability to vary in number and type. (For instance, an appendix may only appear in the offer/contract document for a specific product element.)
| W6 | Offer and Contract Document Administration | FNR 7.4 | Contract documents made by the user, including the metering point list in the Appendix, shall be automatically updated with changes to the contract.
| W6 | Offer and Contract Document Administration | FNR 7.5 | The system shall offer the capability for designated users to categorize documents into super user-defined categories. (e.g. SME, Larger Accounts)
| W6 | Offer and Contract Document Administration | FNR 7.6 | Ørsted wishes to have the possibility of document categorization
| W6 | Offer and Contract Document Administration | FNR 7.7 | The system shall offer the capability within the template generation functionality to handle user-specified conditions.
| W6 | Offer and Contract Document Administration | FNR 7.8 | Ørsted wishes for the template functionality to automatically populate the content based on the specified conditions
| W6 | Offer and Contract Document Administration | FNR 7.9 | The system shall provide the user the ability to select language for the template to be automatically generated in the chosen language (Danish & English) in Denmark
| W6 | Offer and Contract Document Administration | FNR 7.10 | The system shall provide the user the ability to select language for the template to be automatically generated in the chosen language (Swedish & English) in Sweden
| W6 | Offer and Contract Document Administration | FNR 7.11 | The system shall maintain a historical template archive where all versions are stored. All template versions shall be maintained & kept during the lifetime of the system
| W6 | Offer and Contract Document Administration | FNR 7.12 | The system should support template groups including appendices which shall be usable at the product level and across products/sales channels.
| W6 | Offer and Contract Document Administration | FNR 7.13 | Users shall have the ability to specify whether a template is to be used for an offer, contract, or both.
| W6 | Offer and Contract Document Administration | FNR 7.14 | The system shall lock the contract or offer for changes after it has been generated by the user
| W9 | Creating and Renewing Offers | FNR 8.1 | The user shall have the capability to create offers on available products.
| W9 | Creating and Renewing Offers | FNR 8.2 | The user shall have the capability for the same customer to create multiple offers simultaneously, with different periods and products.
| W9 | Creating and Renewing Offers | FNR 8.3 | The user shall be able to search for a customer, select a product and period, and choose relevant surcharges (e.g., DB, bio natural gas, price samples, rate surcharges, etc.).
| Action item of W9 | Creating and Renewing Offers | FNR 8.4 | Ørsted wishes to to explore further usability in the search function as stated in Requirement FNR 8.3 | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Creating and Renewing Offers | FNR 8.5 | Ørsted wishes the supplier to provide different options and possibilities that the users can search for products, customers and relevant surcharges. | Action item of W9 (On Hold): To be finalized after Sales replay session
| W9 | Creating and Renewing Offers | FNR 8.6 | The system shall allow the user to perform volume adjustment, either by indicating absolute volume for relevant delivery periods or as a percentage, shall be possible for all or selected metering points in the offer.
| W9 | Creating and Renewing Offers | FNR 8.7 | The system shall offer the user the capability to add or remove metering points in offer creation.
| W9 | Creating and Renewing Offers | FNR 8.8 | The user shall have the possibility to choose metering points from a previous offer or contract.
| W9 | Creating and Renewing Offers | FNR 8.9 | The user shall have the possibility to recalculate offer commodity prices and fees based on the latest market prices.
| W9 | Creating and Renewing Offers | FNR 8.10 | The system shall allow designated group of users to define different validity period for products in specific channels
| W9 | Creating and Renewing Offers | FNR 8.11 | The system shall ensure that the validity period of any offer aligns with the defined validity period established for each product type.
| W9 | Creating and Renewing Offers | FNR 8.12 | Offer and contract documents shall be automatically generated from the template relevant to the offered product created.
| W9 | Creating and Renewing Offers | FNR 8.13 | A special field shall be provided to write special conditions in the text of the contract and offer.
| W9 | Creating and Renewing Offers | FNR 8.14 | A special field for internal comments not included in the contract or offer shall be available.
| Forecast Logic | Creating and Renewing Offers | FNR 8.15 | The system shall have the ability to calculate and show consumption volumes in the chosen contract period, broken down into meter types (real-time-measured vs yearly/monthly-read) and market price areas (e.g., DK1 and DK2 for power), forecasting from historic volumes based on documented forecast logic.
| Forecast Logic | Creating and Renewing Offers | FNR 8.16 | Ørsted requests that the supplier present their proposed methodologies for forecasting logic.
| W9 | Creating and Renewing Offers | FNR 8.17 | The system shall provide a change log mechanism where it tracks the changes done to the system and from which users. As a minimum changes, contracts and offers.
| W9 | Creating and Renewing Offers | FNR 8.18 | Ørsted desires that the system includes capabilities for monitoring and recording changes. (Products, contracts, offers, templates, user access)
| W9 | Creating and Renewing Offers | FNR 8.19 | The system shall allow the user who prepares the offer (if it is not the account manager) to select the account manager (who is responsible for the offer) as a signee.
| W9 | Creating and Renewing Offers | FNR 8.20 | The system shall provide the capability to allow for different users to be as the signee for an offer, distinct from the user who initiated the offer.
| W9 | Creating and Renewing Offers | FNR 8.21 | Ørsted wishes for the possibility for the system to send the offer/contract directly to a digital signature tool
| W9 | Creating and Renewing Offers | FNR 8.22 | The system shall provide the possibility to recalculate offers, e.g., if the validity of the offer has expired or there is a need to adjust the selling price.
| Forecast Logic | Creating and Renewing Offers | FNR 8.23 | The system shall be able to calculate contracted hourly consumption profile from aggregated metering points' historic consumption data, using a documented forecast method (utilizing consumption patterns, e.g., day in the week, DK/SE bank holidays, etc.). The system shall be able to account also for calendar information in its forecasting logic calculation.
| W9 | Creating and Renewing Offers | FNR 8.24 | The system shall provide users with the capability to download hourly contract volume profiles for each meter type and market price area, as well as market commodity prices, in an exportable format (CSV shall be supported as minimum). This feature allows users to save the data files directly to their local devices for easy access and further analysis, applicable for both offers and contracts
| W9 | Creating and Renewing Offers | FNR 8.25 | The system shall provide the user to possibility to display in the offer the commodity price examples (generated from the price database), e.g., chosen spot product for delivery in the future, indicating the commodity price for the chosen product in the last delivery month.
| W9 | Creating and Renewing Offers | FNR 8.26 | The system shall include an automated data validation functionality that is designed to identify and prevent common data entry errors by the user, ensuring the accuracy and consistency of inputs for offer and contract generation (e.g., preventing the assignment of duplicate metering points)
| W5a | Price Monitoring | FNR 9.1 | The system shall provide the possibility of creating one or more automated price monitoring jobs for a customer. These jobs shall monitor a price for when it has reached a certain user defined pricing range threshold. The prices to be monitored are similar to the product prices in the pricing tool, e.g., Fixed Price. This means no need for price monitoring of external prices.
| W5a | Price Monitoring | FNR 9.2 | The system shall be equipped with a feature that allows for the selection of a recipient who will receive a notification once the pricing job hits the predetermined pricing range threshold set within the monitoring job.
| W5a | Price Monitoring | FNR 9.3 | Ørsted wishes to explore further possibilities with monitoring jobs | Orsted will Rephrase the requirement (On hold)
| W9 | Contracting | FNR 10.1 | Upon signing a customer contract, the system shall enable the user to register the existing offer as "contracted."
| W5 | Contracting | FNR 10.2 | The system shall systematically record the aggregated sold volume across all customers in product-relevant portfolios, with specific portfolios designated for hedging contracted volumes End of Day (EoD) if the product is assigned a hedge portfolio. (Appendix NFR_App_2_ENDUR Integration).
| W5 | Contracting | FNR 10.3 | Ørsted wishes for the possibility to track sold volumes on additional levels than aggregate Ørsted wishes for the possibility to track hedged volumes on contract level.(Contract monthly level). It should be visible in Bit2Win table for Orsted to extract. | Requirement language modified
| W5a | Contract Change Management | FNR 11.1 | The system shall have the functionality to automatically update the metering point list in the contract appendix when changes to the metering point are made in the contract.
| W5a | Contract Change Management | FNR 11.2 | The system shall allow for adjustments in volume, supporting both increases and decreases, for selected metering points and the entire contract.
| W5a | Contract Change Management | FNR 11.3 | The system shall offer the capability to modify the delivery period, allowing for a shortened and extended duration, for selected metering points and the entire contract.
| W9 | Contract Change Management | FNR 11.4 | The system shall provide the capability to select and remove one or more metering points from the contract.
| W5a | Financial Impact of Contract Changes | FNR 12.1 | The system shall be able to calculate and display the financial impact details (e.g., changes in sales margin value, annual subscription, and the value impact) when the user is adding or removing metering points on a fixed price contract. The information shall be displayed separately in a table in the contract details. | Orsted will Rephrase the requirement (On hold)
| W5a | Financial Impact of Contract Changes | FNR 12.3 | The system shall be able to propose to the user a new contract price for fixed prices contract after a contract change. The user shall have the capability to accept this proposed contract price or choose to set a different price, and the system shall display the associated financial impact with the choice. | Orsted will Rephrase the requirement (On hold)
| W9 | Financial Impact of Contract Changes | FNR 12.4 | The system shall dynamically update the displayed financial impact of a contract after each contract change.
| W5 | Hedging | FNR 13.1 | The system shall collect volumes in product portfolios as described in FNR 10.2 designated for hedging and make them available for hedge execution. | Seems like a direct requirement, not discussed in the Workshop
| W5 | Hedging | FNR 13.2 | The system shall be able to provide a hedge overview, displaying all volumes ready for hedging, organized per hedged product portfolio, to allow control by users. | Seems like a direct requirement, not discussed in the Workshop
| W5 | Hedging | FNR 13.3 | The system shall offer the possibility to select one, several, or all portfolios for hedge execution. | Seems like a direct requirement, not discussed in the Workshop
| W5 | Hedging | FNR 13.4 | Upon hedge commitment (execution), hedge details shall be automatically available as CSV files in a pre-defined format. (see Appendix NFR_App_2_ENDUR Integration). | Seems like a direct requirement, not discussed in the Workshop
| W5 | Hedging | FNR 13.5 | The system must ensure that the generated CSV files are automatically stored in a designated location that is readily accessible by Ørsted for further internal control and processing | Seems like a direct requirement, not discussed in the Workshop
| Action item of W9 | Overview of Offers and Contracts | FNR 14.1 | The system shall provide an overview of active offers, enabling users to easily access information on offers currently in progress. (As a minimum the information that needs to be displayed is, Reference number, Product Type, Product, Start Date, End Data, Customer, Valid Until, Account Manager) | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Overview of Offers and Contracts | FNR 14.2 | The system shall offer an overview of contracts finalized, allowing users to efficiently track daily contract activities. (As a minimum the information that needs to be displayed is, Reference number, Product Type, Product, Start Date, End Data, Customer, Valid Until, Account Manager | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Overview of Offers and Contracts | FNR 14.3 | The system shall provide a sorting functionality for the overview of the offers and contracts on all displayed columns. Upon performing a search, the system shall present and list search results, allowing users to view specific subsets of data (e.g., all active offers of salesperson X, all contracts for product A created between date B and date C). | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Overview of Offers and Contracts | FNR 14.4 | The system shall present an overview of contracts modified, providing users with a list of contracts that have recently been changed. | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Overview of Offers and Contracts | FNR 14.5 | The system shall feature a search functionality via the user interface, enabling users to perform searches based on various criteria. | Action item of W9 (On Hold): To be finalized after Sales replay session
| Action item of W9 | Overview of Offers and Contracts | FNR 14.6 | Ørsted wishes for more elaborate possibilities with the search functionality | Action item of W9 (On Hold): To be finalized after Sales replay session
| WR2 | Data and Reporting | FNR 15.1 | The system must give access to data for users and for reporting and integration/ETL tools via APIs that are automatically and dynamically - without need for any kind of development or configuration from Ørsted users - updated to reflect changes in the full application data model.
| WR2 | Data and Reporting | FNR 15.2 | The system must be able to export data for reporting, including but not limited to contract details, customer data, contracted hourly consumption profiles, hedge details, financial impact calculations, metering point data, products, pricing, fees, consumption, etc.
| WR2 | Data and Reporting | FNR 15.3 | Ørsted wishes multiple methods for the data export based in Requirement 15.2
| WR2 | Data and Reporting | FNR 15.4 | There must be direct access to all tables containing Ørsted data or a mirror updated at least once per 24 hours. Ørsted must be able to download data from the system.
| WR2 | Data and Reporting | FNR 15.5 | The system must be able to expose the current content of the full data model via API without the need for development and/or administrations tasks required by Ørsted users to be carried out in advance of the data extraction
| WR2 | Data and Reporting | FNR 15.6 | The supplier shall provide to Ørsted a comprehensive documentation of their system's datal model used for reporting which will be used by Ørsteds data specialists. (Provide the evaluation criteria)
|  | CRM Integration | FNR 16.1 | Ørsted wishes to explore automated offer delivery to Salesforce CRM | Seems like a direct requirement, not discussed in the Workshop |  | I | Integration Strategy
|  | CRM Integration | FNR 16.2 | The system shall expose APIs for bi-directional data synchronization with Salesforce CRM, allowing Ørsted information to be updated in real-time or at scheduled intervals | Seems like a direct requirement, not discussed in the Workshop |  | I
|  | CRM Integration | FNR 16.3 | The pricing tool should support event-based integration using Salesforce APIs, allowing pricing requests to be automatically initiated based on specific triggers or workflows within Salesforce. | Seems like a direct requirement, not discussed in the Workshop |  | I
|  | CRM Integration | FNR 16.4 | The pricing tool should integrate with Salesforce CRM using standard APIs to provide a unified user interface | Seems like a direct requirement, not discussed in the Workshop |  | I
|  | CRM Integration | FNR 16.5 | Supplier must define clear data mapping and transformation rules for API-based data transfer between Salesforce CRM and the pricing tool, ensuring accurate and consistent data synchronization. | Seems like a direct requirement, not discussed in the Workshop |  | I
|  | CRM Integration | FNR 16.6 | The system shall be capable of integrating key business information from Ørsted's Customer Relationship Management (CRM) system. This includes but not limited a variety of essential data points such as the Central Business Register (CVR) number, customer names, physical addresses, contact details, email addresses, and other relevant data. | Integration -Mapping sheet- Ajeesh |  | I
| W17 | GDPR Compliance Functionality | FNR 17.1 | The system shall automatically delete all open offers that are older than a Ørsted specified number of months.
| W17 | GDPR Compliance Functionality | FNR 17.2 | The system shall provide a mechanism to allow the user to delete or anonymize customer data upon request, either for a single costumer or for batch records. | It was the intention is that it would be used by one customer as manual process by the business in exceptional circumstances and therefore we are going to leave it till later as an backlog item |  |  | 1) It will be treated as a manual process for exceptional circumstances where a user can selectively delete specific customer data in Bit2Win. 2) This requirement will be marked as a "good to have" feature and will be addressed through support tickets in the short term. 3) The possibility of developing a GUI for easier access and management of deletions will be considered at a later point.
| W17 | GDPR Compliance Functionality | FNR 17.3 | The system shall include an audit logging feature to document all GDPR-related data processing activities for accountability and traceability. (The audit log data shall not include any GDPR-related data) | Question for Gaetano - In terms of Traceability - Is there a way to extract report for Audit related activities for example - list of accounts that were deleted in last 6 months. Also in Bit2win - do we have any change log where in case if a customer data has been deleted but in change log section it shows somehow the customer name still exits there, so Orsted wanted to make sure that such scenario donot exists
| W17 | GDPR Compliance Functionality | FNR 17.4 | The system shall be capable of processing an external file with lists of CVR numbers that have been anonymized or deleted in Ørsteds billing systems (BFUS and Easy Energy) and or Ørsted CRM system (Salesforce) and shall delete all related data within the Pricing Tool. | Workshop needs to be scheduled between Salesforce developer, Orsted and Wipro team for the GDPR requirements

## Non Functional Requirements
Last Updated On | Workshop ID | Business Process | Req. ID | Requirement | Worshop Discussion | Requirement Met (Y/N) | RICEF | Solution | Design Document Reference | Build Details | Status
| W12 | Data Migration | DAT.10 | Ørsted wishes the supplier to provide a best practice approach for data migration. See Appendix NFR_App_Migration for full requirements and overview of the migration | 1. Orsted wishes to migrate all active contracts including those where a contract is signed but not yet executed – e.g. signed in March, starting in April.​ -- Migrate all the Active contracts 2. Orsted wishes to be able to amend any accounts/contracts that have been migrated​ ​-- Will be discussed in Integration workshops as most of the account details already exists in Salesforce. No Offers (unsigned contracts) are required to be migrated.​ ​-- No offer/unsigned/inactive contracts will not be mattered during the migration. But if the inactive contract account is still open with Orsted then it might be required. Orsted has no requirement to migrate inactive accounts or expired contracts – this means that if a customer left Orsted but returns a year later, their data will not have been migrated.​ ​-- But if the inactive contract account is still open with Orsted then it might be required. Maximum size of legacy data estimated about 400GB (including DK & SE)​ ​-- 400GB is the maximum size of Legacy data but it might get expanded over the course of time. Minimum of 2 years of historical data to be migrated​ -- For consumption data, 2 years of Historic data is enough. But for the forecasting, longer time series might be required.